Project Initiation Kick-off Meeting Minutes

| Project Initiation Kick-off Meeting Minutes | Project: Public awareness and education for development in Europe European Citizens working for the global development agenda Date: 8, 9 April 2009 Time: From: 17:00hrs To: 21:00 hrs From: 15:00hrs To: 18:00 hrs Location: Sofia …. |
| --- | --- |
| Opening: The purpose of the Project Execution Kick-off was to: Formally acknowledge the beginning of Project Execution, Get to know the other team members; Review the project plan. Clarify reciprocal expectations amongst the partners. A second meeting was held the following day to discuss and address more operational project issues. |
| Invitees: …………. |
| Attendees: …………. |
| Minutes over the two day meeting |
|  | Presenter Name | Time (minutes) |
| Introductions |
| Project Background | Stefano De Santis | 40 min |
| Project Goals & Objectives | Stefano De Santis | 30 min |
| Project Methodology | Stefano De Santis | 30 min |
| Economic and financial aspects | Stefano De Santis | 40 min |
| Roles & Responsibilities of the Partners in Romania and Bulgaria | Enzo Reali | 40 min |
| Q&A session | Partners | 60 min |
| Issues that were specifically addressed |
| How do we get the additional 25% required as co-financing? | Partners | 30 min |
| How do we ensure the broad dissemination of the Action Outputs | Partners | 40 min |
| How do we ensure wide participation of stakeholders | Partners | 40 min |
| How do we ensure timely and efficient coordination among partners and effective execution of specific roles, tasks and responsibilities | Partners | 60 min |
| Budget distribution | Partners | 40 min |
| Next steps | Partners | 30 min |
| Additional Information |
| Handouts: | In electronic form: |
| Project Roster |
| Project Gantt |
| European Citizens working for the global development agenda |
| Presentation of the Action: European Citizens working for the global development agenda. |

The meeting started with introductions by partner representatives. Stefano welcomed everyone and explained the NSA-LA budget line of the EC and how this aims at promoting the networking between NSAs and LAs. He then explained the project, its main outputs and activities and budget distribution.

He explained each of the three Action Outputs:

- Three manuals to be developed, one each for educationists, policy makers, media

- 8 Documentaries on MDGs

- Web Portal as a means to distribute the above

He explained that the seminars and meetings will be a channel to use these products. He also stressed that EC would fund 75% and asked partners to contribute to procuring 25% that each partner will have to contribute.

Enzo explained that EU aid to new member states has until now been to build institutional capacity of new governments. Now EC is promoting capacity building  Partnership was an important focus, to help grow private and NGO world. The people trained in the govt. left to join the private and civil society. Enzo explains the importance of time management and the need to utilise the strengths of each organisation

Discussions were done among partners on the content of the products. The stakeholder needs assessment and related research was considered to be the starting point for making the manuals and documentaries. The readership and audience of the Action Outputs will determine the content and communication methodology of outputs.

The products will be developed through a three level approach:

- Working with target groups who need the Action Outputs

- Finding resources and co-producers who will add on and/or contribute to the Action Outputs

- Distributing Action Outputs to cover our funding gaps

Among other things, partners discussed:

- kinds of operating agreements between partners and associates and other third parties

- different categories of stakeholders

- methodologies of approaching stakeholder groups

- methodology of ensuring wider distribution of Outputs

- Gaining wider resonance for Action

- other issues which are detailed below in Action Points

| Decisions |
| --- |
| Decision Made | Impact | Action Required? |
| Web portal | Better coordination, communication, visibility and representative content of Outputs | develop and finalise the Web Portal |
| Defining Stakeholders | Action Outputs will integrate the target group needs and interests | defining better the sub categories of stakeholders to contact and network with understanding better their specific needs and interests of each stakeholder group |
| Networking Activity |  | Getting consensus on Networking Methodology |
| MoUs |  | MoUs among partners to be drafted and signed |
| Issues |
| Issue Description | Impact | Action Required? |
| Confusion of Roles between Bulgarian Partners | No one takes precise responsibility and overlapping of tasks | Clear differentiation and partnership agreement |
| Action Items for Follow Up |
| Tasks Assigned to Implement the Actions Required | Responsible | Target Date |
| Share the Web Site proposal with partners | Armadilla | 25th April 09 |
| Check out the possibility and costs of developing, hosting and managing the Web Portal in their countries | Each Partner | End April 09 |
| Communicate understanding and expectations from the Web Site | Each partner | 20th April 09 |
| Defines the sub categories of stakeholders that it will contact and network | Each partner | end April 09 |
| Send Project Brief to partners for presentation to stakeholders | Armadilla | 20th April 09 |
| Send Project Brief for potential co-producers of the Action Documentaries | Armadilla | End April 09 |
| Detail out plans and tasks of partner contribution to the Action | EUE for Belgian and Bulgarian partners and TEHNE | End April 09 |
| Prepare templates for administrative procedures to be attached to partnership agreement | Kautilya Society | End April 09 |
| Prepare the Partnership Agreements | Armadilla |  |
| Prepare eventual operating agreements third parties as co-producers of Action Documentaries | Armadilla |  |
| Prepare the guidelines for Approval / Signing off Process of expenses and documents | Armadilla |  |
| Share the Web Site proposal with partners | Armadilla | April 09 |
| Sign partnership agreements |  | 10th May 09 |
| Send key guidelines on selecting target groups and individuals | Armadilla | 10th May 09 |
| Send key questions to help partners design either a questionnaire or an interview for understanding stakeholder needs and interests | Armadilla | 10th May 09 |
| Give feedback on key questions sent by Armadilla | Each partner | 15th May 09 |
| Develop the final set of key questions based on feedback of partners | Armadilla | 20th May 09 |
| Identifies and defines the specific needs and interests of each stakeholder group, it contacts and networks with | Each partner | May 09 |
| Conduct interviews or sends out questionnaires | Each partner | May 09 |
| Assess and analyse the needs of the target groups since these will be also the end users of the products | Each partner | May 09 |
| Communicate on tickets and diem assigned to each partner for workshops and conferences | Armadilla | April 09 |
| Prepare eventual operating agreements that partners might have to enter into with third party associates | Kautilya Society and Armadilla | 20th May 09 |
| Conduct interviews or sends out questionnaires | Each partner | May 09 |