## LF - Objectives and results
| Intervention logic | (Outcomes) Objectively verifiable indicators of achievement | Sources and means of verification | Assumptions
Overall objectives | Health determinants of the people living in the District of Koinadugu and their well being is improved . | People's awareness of the health determinants is increased; % increase in households using pit latrines with handwashing facilities; # latrines installed and made operational by the community; Koinadugu District has viable policies in place for sustained provision of basic sanitation, hygiene and safe water to poor, under-served communities; % reduction in child mortality due to diarrhoeal disease; % reduction in incidence rates of diarrhoeal disease; Grade of improvement in school hygiene; # of WASH plans developed during the project for public health/ WASH delivery; # of WASH plans integrated into CDPs during the project; # of Wash plans financed in the district; Quality and Quantity of WASH facilities and services being provided by District Council | UNDP PRS NACSA District Development Plan PRSP Pillar working group report | No significant outbreak of violence within Sierra Leone Government and International Organizations continue to work together in order to support the decentralisation process of water and sanitation services. Community commitment to participated development
Specific objectives | 1. Target communities in Koinadugu, (45 communities, 10 PHUs and 22 schools) have improved access to safe drinking water and can avail of more efficient sanitation facilities and services. | # of water sources developed and made operational; increase in # of schools with available water supply and sanitation; increase in # of Peripheral Health Units with safe water; % increase of people using safe water source for drinking; % increase of persons living within 500m from a WP with a dwelling; # of latrines installed and made operational in the community; % increase in households using latrines; % increase in school children using latrines; % increase of WP serving not more than 450 persons per day; # % increase of households with chronically ill persons (i.e. AIDS patients) having access to safe water; % increase in number of women reporting hygienic disposal of child faeces; % decrease of household pit latrine contaminating a water source. | Ex-ante and ex-post KAP survey Surveillance data where available from DHMT/ MoHS Monitoring data from WSD/ SALWACO PSP water point completion report Water quality test reports District Council reports CHC reports Mid term review report Final Evaluation report | Government of Sierra Leone is supportive to piloting and implementation of appropriate, accessible cost of WASH technologies
| 2. Fortyfive communities in Koinadugu and their leaders become more conscious of the hygiene factors leading to good health and become more aware of the need to foster social cooperation in order to efficiently manage water supply, sanitation services and health education. | Quantity and quality of participatory hygiene education materials developed and distributed; # of Schools have WASH development plans (SHDP); SHC curricula developed; Inclusion of SSHE programmes in the school curriculum wider participation of girls in the programme is encouraged. # of schools receiving weekly PHU health outreach services and # of PHU undertaking EPI programmes % of target population access, use & hygenically maintained sanitary disposal facilities # Schools and # communities adopt disease surveillance and risk reduction schemes in their development plans # of communities and # of families adopting construction of household pit latrines % increase in people washing hands at a minium of 3 out of 5 key times against the baseline survey % increase in people using separate, covered, clean containers with dipping cup/ spoon to store drinking water against the baseline survey results quantity of faecal matter observed on a weekly random transit walk in each community # of CHCs functioning in each of the 30 communities # of recorded cases of spontaneous replication of household latrines based on model promoted by Oxfam and partners % of community members who can state at least 1 behaviour change as a result of the project # persons in communities contributing with unskilled labour | as above School curricula document
| 3. Local authorities and community leaders have a better understanding of the linkages between water, sanitation and hygiene to poverty alleviation, disease reduction and sustainable development and become better capable of planning and implementing policies and actions for sustained delivery of basic sanitation, hygiene and safe water to poor, under-served communities. | Presence of a WASH supervisory and regulatory structure at District Level; District Council designs CDPs that integrate WASH objectives; A PPP is set up between Discrict Council and WDC for O&M of Wash facilites and services; District Council designs CDPs through participatory approach that integrate WASH objectives; Improvement in WASH managerial skills and capacities of Local Authorites and community leaders; Improvement in WASH policy making skills and capacities amongst Local Authorites and community leaders; # of communities that set up and manage a WASH committee; WASH standards have been published by KDC; # of communities that have set up a WASH fund to support WASH activities; Community leaders know contract management and PPP for the utilisation of PSSP services and good governance; Level of feasibility of CDP targets and financial sustainability of the actions envisaged; % of WPs managed by communities and supported by district authorities and local NGOs by end of 2010; Local authorities are succesfull in getting WASH plans financed; Inclusion of SSHE programmes in the school curriculum; Changes in the way local authorities and community leaders actively participate in planning and implementing WASH actions and policies; # of plans for public health/ wat-san delivery across the District | as above
| 4. Local WASH actors acquire more technical capacity for provision and maintenance of WASH related facilities and services. | # of person's capacity build in technical capacity for delivering efficient and integrated WASH services; Trainee Participation in activities aimed at delivering more efficient WASH facilities (objective 1) | progress reports
Expected results | KAP Baseline Report | # of copies distributed | progress reports
| Technical Capacity and Technical Training Needs Report | # of copies distributed | progress reports
| Policy and Advocacy Assessment Report | # of copies distributed | progress reports
| Knowledge resources for technical capacity building of local WASH actors are made available | # of toolkit distributed | progress reports
| The technical capacity of # WASH local actors is increased in delivery and maintenance of WASH related facilities and services | # of WASH actors technically trained Facilities and services for an improved access to clean water more efficient sanitation services in 48 communities in Koinadugu, (including schools and PHU’) are delivered with the active involvement of trainees | progress reports
| Maintenance manuals prepared | # of copies distributed | progress reports
| WASH facilities provided to target communities: - 41 new wells (28 in communities, 8 in schools 5 in PHUs) constructed ; - 49 existing wells rehabilitated (30 in comm 14 in schools 5 in PHUs) ; - 330 VIP latrines installed in 22 schools; - 18 springs boxes constructed; - 22 rain water harvesting structures constructed. - On the job technical training to deliver and maintain efficient WASH services | # of new wells, developed and made operational; # of wells Rehabilitated and made operational; # of springs water sources developed # of rain harvesting structures developed # of springs boxes constructed; % increase of people using safe water source for drinking; % increase of persons living within 500m from a WP with a dwelling; # % increase of households with chronically ill persons (i.e. AIDS patients) having access to safe water; increase in # of schools with available water supply; increase in # of Peripheral Health Units with safe water; improvement in the quality of water in the sources being used daily by target communities. | Pilot study report Physical check/monitoring of water points to ensure they are functional by end of 1st year. Physical check of latrines under construction and in use and through progress and project reports PHU reports of functional CHC | National level wat-san policy development allows for the delivery of appropriate and affordable wat-san services.
| Increase in # of household pit latrines with handwashing facilities. | # of households construction and using pit latrines with handwashing facilities. | progress reports
| 20 WASH technical actors capable of maintaining facilities; | # of toolkits distributed; # of training workshop conducted for # technical actors in maintaining WASH facilities | progress reports
| Spare parts stores set up, equipped and managed for serving 45 communities | # spare parts stores set up, equipped and managed to serve 45 communities | progress reports
| 20 private sectors WASH actors trained in setting up and managing spare parts stores | # of training workshop conducted for in setting up and managing spare parts # persons participating in the training workshop conducted for in setting up and managing spare parts stores # of toolkits distributed | progress reports
| Educational material prepared | # of toolkits distributed | progress reports
| 1500 community members participate in WASH awareness building activities in the communities | # persons who participate in WASH awareness building activities (events, campaigns, etc.) # of events / campaigns held, # of participants; # of toolkits distributed+C4 | progress reports SHC activity cards
| 1500 children participate in WASH awareness building activities in school | # children who participated in school activities # of events / campaigns held, # of participants; # of toolkits distributed % of schools have a school health club. | progress reports SHC activity cards
| 750 school girls who participated and contributed to school activities | # school girls who participated and contributed to school activities | progress reports
| 45 community health clubs are established in all target communities | # of community health clubs are established in all target communities % of communities having at least 1 community health club. | progress reports CHC activity cards
| 45 sessions for CHCs on gender awareness focused on youth to address gender issues in the community | # sessions for CHCs on gender awareness focused on youth to address gender issues in the community | progress reports
| Local authorities and community leaders have a better understanding of the linkages between water, sanitation and hygiene to poverty alleviation, disease reduction and sustainable development | # of workshops and/or sensitization events held, # of participants; # of toolkits distributed | progress reports | National and governmental actors such as WSD and SALWACO are able to take on effective role in rural water development in context of decentralisation
| Local authorities, community leaders and opinion makers become aware of the importance of girls' education and gender equality as a necessary complement to the success of water and sanitation infrastructure projects | # of workshops and/or sensitization events held, # of participants; # of toolkits distributed | Reports of: ~ Visits to communities as selected by district council. ~ Focus group discussions. ~ Meetings with CBOs, committees, and head of households including women households with (50:50) representation
| The capacity of local authorities and community leaders in increased in on management issues of WASH facilities and services delivery (including contract management and PPP for the utilisation of PSSP services and good governance) | # of training events held, # of participants; # of toolkits distributed Level of post training technical capacity; | -Koinadugu District Development Plan (rolling plan) -Koinadugu District Council reports | District government authorities receptive to collaboration with Oxfam and partner organisations
| Recommendations and guidelines are prepared for including in the District Development Plan the lessons learnt with the communities on how to improve the District hygienic conditions and the management of water distribution and sanitation services | Recommendations ang guidelines prepared; # target distribution of recommendations ang guidelines achieved; # of training events held, # of participants; # of toolkits distributed. | progress reports
| Local authorities are supported in preparing WASH plans and in developing operation and maintenance and financing scheme | # of training events held, # of participants; # of toolkits distributed Level of post training technical capacity; # of districts with a work plan defined in a participatory process linked to the MOU; # of toolkits distributed | Community training meetings and reports workshop reports
| Report of ex post KAP survey | # of report copies distributed among stakeholders | progress reports
| mid term review | report ready | progress reports
| Summative evaluation report | # of report copies distributed among stakeholders | progress reports
| Project Results are shared through an experience sharing workshop | # of report copies distributed among stakeholders | progress reports

## Activities and Work Plan
Activity | Results / Milestones | Resources (besides OGB and partners personnel and offices) | Cost of Resources required (besides OGB and partners office and personnel) | first year | [11 empty] | second year
Initial activities |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 1 0 | 1 1 | 1 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 1 0 | 1 1 | 1 2
Establishment of project Team | Project team created | bar: first year 1
Induction of Project Team | Induction Report | bar: first year 1
Selection of communities and partners | Local communities selected and MoUs signed Local partners selected and MOUs signed | bar: first year 2 to first year 3
Detailed assessment of WASH resources and needs | WASH Baseline Report Technical Capacity and Technical Training Needs Report Policy and Advocacy Assessment Report | bar: first year 2 to first year 6
Setting up a WASH committee | WASH committee formed | bar: first year 2
To deliver improved WASH services to the communities and build the related technical capacity of local WASH actors |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 1 0 | 1 1 | 1 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 1 0 | 1 1 | 1 2
Selection of trainees amongst local WASH actors | Technical Trainee selection report | bar: 3
Preparing the Technical capacity building plan | CB Plan for Technical training | bar: 3
Collection and Development of training material and resources | Training resources and materials ready and maintenance manuals prepared | bar: 3
Stakeholder participated identification of appropriate locations for WASH facilities and services | Report on stakeholder participated identification of appropriate locations for WASH facilities and services | bar: 3
Procurement of required hardware and equipment for WASH facilities | hardware and equipment procured- equipment list ready | bar: 5
Construction of new wells (28 in communities, 8 in schools 5 in PHUs); Rehabilitation of existing wells (30 in comm, 14 in schools, 5 in PHUs). | Project launch event organized and attended by # persons 41 new wells (28 in communities, 8 in schools 5 in PHUs) constructed 49 existing wells rehabilitated (30 in comm, 14 in schools, 5 in PHUs) 330 VIP latrines constructed and made operational in 22 schools 18 springs boxes constructed 22 rain water harvesting structures constructed # of household that have participated in the # events organized for explaining how to make pit latrines with hand washing facilities # persons in communities providing unskilled labour as contribution for WASH facilities | Skilled labour (168 person weeks) Unskilled labour (community contribution for 2496 person weeks) External facilitators for workshops and events (2 weeks) DSA for participation in workshops and events (164) Materials and Tools for construction of 330 blocks of 2-drop hole ventilated pit latrines in 22 schools Materials and Tools for 41 new Hand Dug Wells Materials and Tools for Rehabilitation of 49 Wells Materials and Tools for 18 spring boxes Materials and Tools for 22 rain water harvestign structures Accommodation for participants in workshops and events Transport for participants workshops and events Other costs for workshops/event management Tool kits and other training resources (21) T-shirts (100) Sign boards (120) | 1051518 | bar: 4 to 7
Teaching people how to construct household pit latrines. | % increase of household pit latrines with handwashing facilities # latrines installed and made operational by the community; | bar: 6
Technical training for O&M of WASH facilities | WASH technical actors capable of maintaining facilities; 1 training workshop conducted for 20 persons | External facilitators for workshops and events (1 week), DSA for participation in workshops and events (40), Food and accommodation for participants to workshops and events (40), Transport for participants to workshops and events (40), Other costs for workshops/event management, Tool kits and other training resources (20), T-shirts (20) | 5130 | bar: 9 to 1 0
Understand the demand for spares for WASH facilities and market research on private service providers and spare parts supply capacity | Document indicating identified spare parts demands and supply sources | bar: 4 to 7
Training private sector in managing spare part stores | 1 training workshop conducted for 20 persons | External facilitators for workshops and events (1 week); DSA for participation in workshops and events (40); Food and accommodation for participants to workshops and events (40); Transport for participants to workshops and events (40); Other costs for workshops/event management; Tool kits and other training resources (20); T-shirts (20) | 5130 | bar: 8
Setting up Spare parts stores | # of spare parts stores established serving 45 communities 1 training workshop conducted for 20 persons | pre-finances of spare parts for community (45); cash boxes (45) | 25200 | bar: 9 to 1 0
Teaching basic sanitation and hygiene to 45 communities and school children of 22 schools, with a particular focus on girls' education and gender equality, as a necessary complement to the success of water and sanitation infrastructure projects. |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 1 0 | 1 1 | 1 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 1 0 | 1 1 | 1 2
Collection and preparation of participatory hygiene education and awareness building materials | awareness material resources ready | bar: 3
Preparing along with the partners a plan for awareness building activities in schools and communities and of teacher training activities | Plan ready | bar: 3
Hygiene awareness building and health promotion in 45 target communities | 6 awareness building workshops and/or events and campaigns conducted, # persons participating; 45 Community health clubs are established in all target communities; curricula developed for CHC; Refresher training for # PHU staff done in 10 PHUs on healthy villages and school sanitation and hygiene; 45 sessions on gender awareness focused on youth; # of Health and hygiene sessions held in CHCs and # of participants; | External facilitators for workshops and events (8.4 weeks); DSA for participation in workshops and events (900); Accommodation for participants in workshops and events; Transport for participants to workshops and events (900); Other costs for workshops/event management (6); Billboards (90); T-shirts (900); Radio campaigns (per 12 month) | 57300 | bar: 4 to 9
Hygiene awareness promotion in 22 schools; Sensitisation of Parent and Teacher Associations and school authorities | 6 awareness building workshops and/or events and campaigns conducted and # persons participating; # of children engaged in participating in school activities centred on C2C and hygiene awareness as part of the school curriculum; # of school girls participating and contributing to school activities; curricula developed for SHC; # SLTS programmes set up in 22 schools; # of School children adopt a family to encourage CLTS in the communities; 22 School Health Clubs (SHCs) created | External facilitators for workshops and events (7.2 weeks); DSA for participation in workshops and events (450); Accommodation for participants in workshops and events; Transport for participants to workshops and events (450); Tool kits and other training resources (450); Other costs for workshops/event management (6); Billboards (45); T-shirts (450) | 85800 | bar: 4 to 3
To reinforce the political will to prioritize the provision of basic sanitation, hygiene and safe water to under-served communities and support District councils to plan and implement integrated plans for improving the fundamental health determinants in the districts. |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 1 0 | 1 1 | 1 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 1 0 | 1 1 | 1 2
Detailing plan for policy sensitisation, managerial training and policy support activities for WASH policies | Plan Ready 1 consultation event organised | Other costs for event management | 500 | bar: 6
Policy sensitization among local authorities and community leaders on: - linkages between water, sanitation and hygiene to poverty alleviation, disease reduction and sustainable development; - importance of girls' education and gender equality as a necessary complement to the success of water and sanitation infrastructure projects | 2 sensitization events held, each for 45 participants; Local authorities and community leaders have a better understanding of the linkages between water, sanitation and hygiene to poverty alleviation, disease reduction and sustainable development; Local authorities, community leaders and opinion makers become aware of the importance of girls' education and gender equality as a necessary complement to the success of water and sanitation infrastructure projects | External facilitators for workshops and events (2.4 weeks); DSA for participation in workshops and events (90); Accommodation for participants in workshops and events; Transport for participants to workshops and events (90); Other costs for workshops/event management (2); Tool kits and other training resources (90); Signboards (45); T-shirts (130); Radio campaigns (per 12 month) | 20030 | bar: 7 to 1 0
Training local authorities and community leaders on management issues of WASH facilities and services delivery (including contract management and PPP for the utilisation of PSSP services and good governance) | 2 training events organized, each for 45 participants Training Reports capacity of local authorities and community leaders is increased in contribution to planning and implementing of actions and policies for sustained delivery of basic sanitation, hygiene and safe water to poor marginalised communities | External facilitators for workshops and events (2.4 weeks); DSA for participation in workshops and events (90); Accommodation for participants in workshops and events; Transport for participants to workshops and events (90); Other costs for workshops/event management (2); Tool kits and other training resources (90); T-shirts (130) | 17780 | bar: 1 1 to 1 2
Preparing and presenting recommendations and guidelines for facilitating preparation of District Development Plan based on lessons learnt with the communities on how to improve the District hygiene conditions and the management of water distribution and sanitation services | Recommendations and guidelines are prepared and presented to stakeholders; 3 consultation events held; 3 presentation events held | External facilitators for workshops and events (1 week); DSA for participation in workshops and events (90); Accommodation for participants to workshops and events (90); Transport for participants to workshops and events (90); Other costs for workshops/event management (6); Tool kits and other training resources (90); T-shirts (130) | 19930 | bar: 1 to 3
Supporting District Council in planning and implementing integrated plans for improving the fundamental health determinants in the districts | 5 events held; Local authorities are supported in preparing WASH plans and in developing O&M and financing schemes; District has a work plan defined in a participatory process linked to the MOU | DSA for participation in workshops and events (100) Accommodation for participants in workshops and events; Transport for participants to workshops and events (100); Other costs for workshops/event management (5); Tool kits and other training resources (100); Signboards (10); T-shirts (130) | 19300 | bar: 3 to 9
Final evaluation and dissemination activities |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 1 0 | 1 1 | 1 2 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 1 0 | 1 1 | 1 2
Overall supervision, auditing, monitoring and evaluation. | Mid term review Summative Evaluation Report
Ex post KAP survey | report | bar: 1 0 to 1 1
Promoting the dissemination of results and replication of the pilot activities carried out | Results of the delivery of water technologies, provision of sanitation infrastructure and of the pilot management approach are presented to stakeholders and are organized for policy recommendations | bar: 9 to 1 2
Total Cost of Resources (besides OGB and partners office and personnel) |  |  | 1307619
Total Field office, logistics and administrative services |  |  | 662950
Total Direct Personnel cost |  |  | 1423597.2433
Total Project Support Cost |  |  | 388394.9455
Grand Total |  | Total project | 3782561.1888

## Budget
Budget |  |  | Unit | Unit cost | Quantity | Total cost
Direct Implementation Costs | Resources (besides OGB and partner personnel and offices) | Materials, Tools and Equipment for construction of new Hand Dug Wells | per new Hand Dug Well | 6597.9333 | 41 | 270515.2667
|  | Materials, Tools and Equipment for Rehabilitating wells | per Rehabilitated Well | 3358 | 49 | 164542
|  | Materials, Tools and Equipment for construction of 2-drop hole ventilated pit latrines | per latrine block | 1449.3333 | 330 | 478280
|  | Materials, Tools and Equipment for spring boxes | for each box | 2700 | 18 | 48600
|  | Materials, Tools and Equipment for Rain water harvesting | for each Rain water harvesting structure | 1800 | 22 | 39600
|  | Accommodation for participants to workshops and events | per person/day | 10 | 1820 | 18200
|  | Transport for participants to workshops and events | per person/day | 7 | 1841 | 12887
|  | Other costs for workshops/event management | per event | 500 | 32 | 16000
|  | Tool kits and other training resources | per toolkit | 120 | 891 | 106920
|  | Billboards | 1 | 100 | 135 | 13500
|  | Signboards | 1 | 30 | 175 | 5250
|  | T-shirts | 1 | 10 | 2010 | 20100
|  | Radio campaigns | (per month) | 100 | 24 | 2400
|  | pre-finance spare parts for community | lump | 550 | 45 | 24750 | \
|  | cash box | 1 | 10 | 45 | 450
|  | Skilled labour (builders fee) | person /day | 3.4 | 1408 | 4787.2
|  | Unskilled labour (community contribution) | ` | 1.7 | 19016 | 32327.2
|  | External facilitators for workshops and events | person /day | 127 | 150 | 19050
|  | DSA for participation in workshops and events | day | 15 | 1964 | 29460
|  | Total Resources (besides OGB and partner personnel and offices) |  |  |  | 1307618.6667
| Field office, logistics and administrative services | Furniture fixture and Equipment
|  | Furniture fixture (Oxfam) (see attached) | office | 3150 | 1 | 3150
|  | Furniture and Fixture (partners) | lump sum | 9000 | 1 | 9000
|  | Computers (Oxfam) | lump sum | 9600 | 1 | 9600
|  | VSAT/Network and Server | lump sum | 52500 | 1 | 52500
|  | Computers (partners) | per item | 8700 | 1 | 8700
|  | Generator (Oxfam) | lump sum | 18000 | 1 | 18000
|  | Generator (partners) | per item | 12000 | 3 | 36000
Vehicle
|  | Hardtop | per item | 48000 | 4 | 192000
|  | Truck for procurement distribution | per item | 80000 | 1 | 80000
|  | Pick-up | per item | 45000 | 1 | 45000
|  | Motorbikes | per item | 2500 | 8 | 20000
Vehicle Maintenance and Fuel cost
|  | Vehicle Maintenance Oxfam - field | vehicle per month | 350 | 60 | 21000
|  | Vehicle Maintenance - partner | vehicle per month | 350 | 60 | 21000
|  | Motorbike maintenance | vehicle per month | 75 | 160 | 12000
|  | Fuel - Vehicle - Oxfam field | vehicle per month | 450 | 60 | 27000
|  | Fuel - Vehicle - Partner | vehicle per month | 350 | 60 | 21000
|  | Fuel - motorbikes | vehicle per month | 100 | 160 | 16000
Rental, Utilities and communications
|  | Office rental - Kabala Oxfam | month | 250 | 24 | 6000
|  | Office maintenance - Oxfam | month | 100 | 24 | 2400
|  | Office establishment/repair costs - Oxfam | lump sum | 3000 | 1 | 3000
|  | Office rental - Kabala partners | month | 150 | 66 | 9900
|  | Office maintenance - Partners | month | 50 | 66 | 3300
|  | Office establishment/repair costs - Partners | item | 1000 | 3 | 3000
|  | Water cost - Partners | item | 30 | 66 | 1980
|  | Water cost - Oxfam | month | 30 | 24 | 720
|  | Generator fuel -Oxfam | month | 200 | 24 | 4800
|  | Generator Fuel partner | month | 200 | 66 | 13200
|  | Communication - Oxfam | month | 350 | 24 | 8400
|  | communication - partners | month | 650 | 22 | 14300
|  | Total Field office, logistics and administrative services |  |  |  | 662950
| Direct Personnel cost Oxfam Koinadugu and Partners | Program Manager (Oxfam) | person /month | 7453.9349 | 24 | 178894.4383
|  | Public Health Coordinator (Oxfam) | person /month | 1200 | 24 | 28800
|  | Business Development Officer (Oxfam) | person /month | 1200 | 24 | 28800
|  | Public health mobiliser (Oxfam) | person /month | 1200 | 24 | 28800
|  | Wash Engineer (Oxfam) | person /month | 1200 | 24 | 28800
|  | Finance Officer (Oxfam) | person /month | 650 | 24 | 15600
|  | Logistics Officer (Oxfam) | person /month | 650 | 24 | 15600
|  | HR Officer (Oxfam) | person /month | 650 | 24 | 15600
|  | Cleaner Officer (Oxfam) | person /month | 345.5319 | 24 | 8292.765
|  | Drivers (Oxfam) | person /month | 478.4287 | 24 | 11482.29
|  | Project Coordinator (1 for each partner) | person /month | 1483.5 | 60 | 89010
|  | Public Health Coordinators (1 for each one of the 3 partners) | person /month | 1236.25 | 60 | 74175
|  | WASH Coordinator (2 for each one of the 3 partners) | person /month | 989 | 240 | 237360
|  | Public Health Technicians (4 for each one of the 3 partners) for each partner) | person /month | 650 | 240 | 156000
|  | Public Health Mobilisers (4 for each one of the 3 partners) | person /month | 650 | 240 | 156000
|  | Behavioural Change Officers (1 for each one of the 3 partners) | person /month | 650 | 60 | 39000
|  | Finance Admin HR (1 for each one of the 3 partners) | person /month | 500 | 60 | 30000
|  | Logistics (partner) (1for each partner) | person /month | 500 | 60 | 30000
|  | Driver (1 for each one of the 3 partners) | person /month | 432.6875 | 60 | 25961.25
|  | Cleaner (1 for each one of the 3 partners) | person /month | 346.15 | 60 | 20769
|  | Guard (2 for each one of the 3 partners) | person /month | 432.6875 | 120 | 51922.5
Consultancy for Scale Up
|  | Ext. consultant for M&E | person /month | 10000 | 1 | 10000
|  | Ext. consultant for Market Research | person /month | 7000 | 1 | 7000
|  | Ext. consultant for budget tracking | person /month | 3000 | 3 | 9000
|  | Ext WASH consultant | person /month | 7000 | 1.5 | 10500
|  | External Logistics / HR consultant | person /month | 7000 | 3 | 21000
|  | Ext Public Health consultant | person /month | 7000 | 1.5 | 10500
|  | External consultant for well augering | person months | 1.5 | 600 | 900
Travel
|  | International air travel | per journey | 2500 | 14 | 35000
Diem
|  | Diem for expatriate staff | per day | 150 | 179 | 26850
|  | Diem for national staff (within SL) | per day | 120 | 144 | 17280
|  | Diem for HQ staff in field | per day | 20 | 235 | 4700
|  | Total Direct Personnel cost |  |  |  | 1423597.2433
| Total Direct Implementation Costs = |  |  |  |  | 3394165.91
Project Support Cost | Oxfam Freetown and HQ | Country Director 22% | person /month | 9800 | 5 | 49000
|  | Finance Manager/Deputy Country Director 25% | person /month | 9533 | 6 | 57198
|  | HR Manager 22% | person /month | 4697 | 5 | 23485
|  | Senior Logistics Officer 22% | person /month | 2472 | 5 | 12360
|  | Senior Finance Officer 22% | person /month | 3956 | 5 | 19780
|  | Driver 25% | person /month | 1672 | 6.25 | 10450
|  | Hardtop car for HQ (25%) | per car | 48000 | 0.25 | 12000
|  | Vehicle maintenance and fuel | per month | 2000 | 6 | 12000
|  | Rental, Utilities and communications (20%) | per month | 2500 | 4.8 | 12000
|  | HQ overheads | 5% of Project cost |  |  | 180121.9455
| Total Project Support Cost = |  |  |  |  | 388394.9455
Total Project Cost = | [5 empty] | 3782560.8555
Funding Source
|  | Community contribution (unskilled labour) |  |  |  | 32327.2
|  | UNICEF |  |  |  | 3750233.6555
|  | Total |  |  |  | 3782560.8555

## WASH service provision
Location | number of | New wells | Rehabilitated wells | blocks of 2 stand VIP latrines | Spring boxes | Rain Water harvesting
Community | 45 | 28 | 30 | 0 | 18 | 0
Schools | 22 | 8 | 14 | 330 | 0 | 22
PHU | 10 | 5 | 5 | 0 | 0 | 0
Total in 3 Chiefdoms |  | 41 | 49 | 330 | 18 | 22
Total direct cost (besides Oxfam and partners personnel and field offices) |  |  |  |  | 913337.2667

## Construction budget details
ITEM DESCRIPTION | Unit specification |  | UNIT COST ($) | # of units per new well (15m) | # of units per Rehabilitation wells (15m) | # of units per 1 block of 2 stand VIP latrine | Cost of requirement of this item for each new well | Cost of requirement of this item for each Rehabilitated well | Cost of requirement of this item for 1 block of 2 stand VIP latrine
Materials
Cement lining | bag | 3.5/m | 12 | 52.5 | 17.5 | 3 | 630 | 210 | 36
Cement Casing | bag | 3/m | 12 | 15 | 15 | 0 | 180 | 180 | 0
Finishing | bag |  | 12 | 3 | 3 | 0 | 36 | 36 | 0
Apron/drainage channel | bag |  | 12 | 8 | 8 | 0 | 96 | 96 | 0
Mouldings (1 set / 5 wells) | set |  | 3500 | 0.2 | 0 | 0 | 700 | 0 | 0
Re-rods (6 mm) | length |  | 8 | 30 | 10 | 0 | 240 | 80 | 0
Re-rods (8mm) | length |  | 10 | 0 | 0 | 5 | 0 | 0 | 50
Binding Wire (small roll 25kg) | roll |  | 36.6667 | 1 | 1 | 1 | 36.6667 | 36.6667 | 36.6667
Sand Mining | trip | 72hp | 1 | 216 | 100 | 216 | 216 | 100 | 216
Stone (aggregate) Mining | trip | 120hp | 1 | 360 | 100 | 240 | 360 | 100 | 240
ballstone | trip | 120hp | 0.5 | 120 | 60 | 0 | 60 | 30 | 0
Blocks (Latrine pit) | piece | 9' | 1 | 0 | 0 | 100 | 0 | 0 | 100
Blocks (Foundation and Superstructure) |  | 5' | 1 | 0 | 0 | 150 | 0 | 0 | 150
Timber | length | 1x12x14 | 4 | 0 | 0 | 3 | 0 | 0 | 12
Timber | length | 2x3x14 | 2 | 0 | 0 | 3 | 0 | 0 | 6
Timber | length | 2x4x14 | 2 | 0 | 0 | 2 | 0 | 0 | 4
Timber | length | 1x9x14 | 2 | 0 | 0 | 2 | 0 | 0 | 4
Timber | length | 2x6x14 | 4 | 0 | 0 | 2 | 0 | 0 | 8
India Mark II Hand Pump | pump |  | 1553.9333 | 1 | 0 | 0 | 1553.9333 | 0 | 0
Tool box | set |  | 300 | 1 | 1 | 0 | 300 | 300 | 0
spares | set |  | 450 | 1 | 1 | 0 | 450 | 450 | 0
wire nails | packet | 2' | 2 | 0 | 0 | 1 | 0 | 0 | 2
wire nails | packet | 3' | 2 | 0 | 0 | 1 | 0 | 0 | 2
wire nails | packet | 4' | 2 | 0 | 0 | 1 | 0 | 0 | 2
wood preservative | gallon |  | 13 | 0 | 0 | 1 | 0 | 0 | 13
Thinner | gallon |  | 11 | 0 | 0 | 1 | 0 | 0 | 11
CI sheets (8ft) | bundle | 20 sheets | 7 | 0 | 0 | 8 | 0 | 0 | 56
Roofing nails | box |  | 5 | 0 | 0 | 1 | 0 | 0 | 5
Emulsion paint | gallon |  | 7 | 0 | 0 | 1 | 0 | 0 | 7
Oil paint | gallon |  | 15 | 0 | 0 | 2 | 0 | 0 | 30
whitewash | bag |  | 5 | 0 | 0 | 1 | 0 | 0 | 5
Accessories VIP latrine
mesh | yard |  | 2 | 0 | 0 | 1 | 0 | 0 | 2
wash basin Without accessories) | piece |  | 30 | 0 | 0 | 2 | 0 | 0 | 60
Taps (3/4") | piece |  | 8 | 0 | 0 | 2 | 0 | 0 | 16
Socket (3/4") | piece |  | 1.5 | 0 | 0 | 4 | 0 | 0 | 6
Drain Plug | piece |  | 7 | 0 | 0 | 2 | 0 | 0 | 14
hand washing tank and cover | piece |  | 12 | 0 | 0 | 2 | 0 | 0 | 24
Vent Pipes (4" PVC) | length |  | 27 | 0 | 0 | 1 | 0 | 0 | 27
Elbow pipe (4" PVC) | piece |  | 4 | 0 | 0 | 2 | 0 | 0 | 8
Total Materials | [6 empty] | 4858.6 | 1618.6667 | 1152.6667
Tools
Pick axe with handle | piece |  | 8.3333 | 1 | 1 | 2 | 8.3333 | 8.3333 | 16.6667
Shovels | piece |  | 10 | 4 | 4 | 4 | 40 | 40 | 40
Headpan | piece |  | 6 | 8 | 8 | 2 | 48 | 48 | 12
Wheel Barrow | piece |  | 36.6667 | 1 | 1 | 1 | 36.6667 | 36.6667 | 36.6667
Tape Measure (30m) | piece |  | 8.3333 | 1 | 1 | 1 | 8.3333 | 8.3333 | 8.3333
Tape Measure (5m) | piece |  | 3.3333 | 2 | 2 | 2 | 6.6667 | 6.6667 | 6.6667
Plumb ball and line | piece |  | 11.6667 | 1 | 1 | 0 | 11.6667 | 11.6667 | 0
Spirit level (4ft) | piece |  | 8.3333 | 1 | 1 | 0 | 8.3333 | 8.3333 | 0
Plier | piece |  | 5 | 1 | 1 | 1 | 5 | 5 | 5
Manilla rope | length |  | 150 | 2 | 2 | 0 | 300 | 300 | 0
Safety block pulley - 2 way | piece |  | 150 | 1 | 1 | 0 | 150 | 150 | 0
Hand gloves | pair |  | 5 | 6 | 6 | 0 | 30 | 30 | 0
Hack saw frame | piece |  | 6.6667 | 1 | 1 | 1 | 6.6667 | 6.6667 | 6.6667
Hack saw blade | set |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
Angle iron | piece |  | 46.6667 | 2 | 2 | 2 | 93.3333 | 93.3333 | 93.3333
Wire brush | piece |  | 2.6667 | 2 | 2 | 1 | 5.3333 | 5.3333 | 2.6667
Marlet | piece |  | 16.6667 | 2 | 2 | 1 | 33.3333 | 33.3333 | 16.6667
Trowel (small) | piece |  | 1 | 2 | 2 | 1 | 2 | 2 | 1
Trowel (large) |  |  | 2 | 0 | 0 | 1 | 0 | 0 | 2
Safety helmet | piece |  | 5 | 4 | 4 | 0 | 20 | 20 | 0
Bucket (34 local made) | piece |  | 7.3333 | 4 | 4 | 0 | 29.3333 | 29.3333 | 0
Galvanised Bucket (28) | piece |  | 5 | 0 | 0 | 1 | 0 | 0 | 5
Sledge hammer | piece |  | 26.6667 | 2 | 2 | 0 | 53.3333 | 53.3333 | 0
Goat hammer |  |  | 7 | 0 | 0 | 2 | 0 | 0 | 14
Paint Brush | 2' |  | 1 | 0 | 0 | 2 | 0 | 0 | 2
| 3' |  | 1.5 | 0 | 0 | 2 | 0 | 0 | 3
| 4' |  | 2 | 0 | 0 | 2 | 0 | 0 | 4
Cross cut saw |  |  | 5 | 0 | 0 | 1 | 0 | 0 | 5
Panel saw |  |  | 5 | 0 | 0 | 1 | 0 | 0 | 5
Giant cutter |  |  | 10 | 0 | 0 | 1 | 0 | 0 | 10
Total Tools | [6 empty] | 897.3333 | 897.3333 | 296.6667
Equipments
Mouldings to rent | month | day | 4.5 | 14 | 14 | 0 | 63 | 63 | 0
Dewatering hire | day | 3 days | 85 | 3 | 3 | 0 | 255 | 255 | 0
Fuel for dewatering | gallon | 3 days | 5.5 | 2 | 2 | 0 | 11 | 11 | 0
Hydratech oil | Litre |  | 3 | 1 | 1 | 0 | 3 | 3 | 0
Transportation | trip |  | 170 | 3 | 3 | 0 | 510 | 510 | 0
Total Equipments | [6 empty] | 842 | 842 | 0
Total requirement for each facility | [6 empty] | 6597.9333 | 3358 | 1449.3333
New Well | Unit |  | Unit cost |  | # of items |  | Cost
Materials | 1 new well |  | 4858.6 |  | 41 |  | 199202.6
Tools | 1 new well |  | 897.3333 |  | 41 |  | 36790.6667
Equipment | 1 new well |  | 842 |  | 41 |  | 34522
total each new well |  |  | 6597.9333 |  | 41 |  | 270515.2667
Rehabilitated well | Unit |  | Unit cost |  | # of items |  | Cost
Materials | 1 rehabilitated well |  | 1618.6667 |  | 49 |  | 79314.6667
Tools | 1 rehabilitated well |  | 897.3333 |  | 49 |  | 43969.3333
Equipments | 1 rehabilitated well |  | 842 |  | 49 |  | 41258
total each new wells |  |  | 3358 |  | 49 |  | 164542
VIP latrine | Unit |  | Unit cost |  | # of items |  | Cost
Materials | 1 block of 2 latrines |  | 1152.6667 |  | 330 |  | 380380
Tools | 1 block of 2 latrines |  | 296.6667 |  | 330 |  | 97900
Equipments | 1 block of 2 latrines |  | 0 |  | 330 |  | 0
total |  |  | 1449.3333 |  | 330 |  | 478280
Other structures | Unit |  | Unit cost |  | # of items |  | Cost
Spring boxes | 1 box |  | 2700 |  | 18 |  | 48600
Rain water harvesting | 1 rwh structure |  | 1800 |  | 22 |  | 39600
total |  |  |  |  | 40 |  | 88200
Total direct cost (besides Oxfam and partners personnel and field offices) | [7 empty] | 913337.2667