## Stakeholders Analysis
Stakeholders Analysis
EA Number: 34040K
District/Cty/Rte/PM: 08-SBD-395-0.5
Project Manager: Lisa Gonzales
RBS Group | Function | Name | Telephone | Stakeholders Goals on this Project | Preferred Method of Communication | Second Preferred Method of Communication | Preferred Method for Rewarding the Team
106 | Project Management | Lisa Gonzales | (909) XXX-XXXX | Efficient project completion | email | cell phone | Team Celebration
140 | Project Management | Peggy Wright | (909) XXX-XXXX | Project completed within cost, scope and schedule | email | telephone | Team Celebration
146 | Program Management | Robert Johnson | (909) XXX-XXXX | Keep project on track | email | telephone | Certificate
147 | Capital Outlay Mgmt | Fred Carter | (909) XXX-XXXX | Secure funding | email | telephone | Team Celebration
168 | Envr-Biological/Permits | Slandra Vijay | (909) XXX-XXXX | Having all mitigation completed | email | telephone | Team Celebration
170 | Envr-Mgmt | Jim Black | (909) XXX-XXXX | Environmental requirements covered | email | cell phone | Team Award
178 | Envr-Cultural | Paul Hernandez | (909) XXX-XXXX | Complete mitigation | email | cell phone | Team Award
195 | Forecasting | David Blake | (909) XXX-XXXX | To produce accurate data | email | in person | Team Celebration
233 | Design P | Abdulla Fathi | (909) XXX-XXXX | Quality design plans | telephone | email | Team Celebration
236 | Design I | Wendy Young | (909) XXX-XXXX | Meet the functional design requirements | cell phone | email | Team Award
303 | Agreements | Cathy Pickett | (909) XXX-XXXX | Clear and concise agreements | email | telephone | Certificate
308 | Surveys/RW Engineering | Nasreem Maljai | (909) XXX-XXXX | Accurate and timely right of way maps and deeds | email | telephone | Team Celebration
312 | Hydraulics | Ron Ho | (909) XXX-XXXX | No change orders/As-Builts | email | telephone | Team Celebration
327 | Materials Engineering | Ken Lee | (909) XXX-XXXX | Minimum amount of retesting | email | telephone | Team Celebration
332 | Envr-Engineering | Norma Sanchez | (909) XXX-XXXX | To find acceptable mitigation sites | email | telephone | Team Celebration
340 | L/S Architecture – Br. A | Peter Tanaka | (909) XXX-XXXX | Public Support | email | telephone | Team Award
341 | L/S Architecture – Br. B | Loren Bird | (909) XXX-XXXX | Positive feedback from the public | email | telephone | Team Celebration
351 | Truck Service Manager | Susan Wong | (909) XXX-XXXX | No equipment delays | email | telephone | Team Celebration
365 | Operations Services | Mark Brown | (909) XXX-XXXX | No traffic accidents | email | telephone | Team Celebration
368 | Operations-Surveillance | Amanda Flores | (909) XXX-XXXX | Positive feedback from the public on traffic lane closures | email | telephone | Team Award
370 | Transportation Mgmt | Kamal Ghol | (909) XXX-XXXX | No complaints from the public | email | telephone | Team Celebration
375 | TMP/District Traffic | Yang So | (909) XXX-XXXX | No traffic accidents | email | telephone | District Director Recognition
380 | Traffic Design – SBD | Anita Moore | (909) XXX-XXXX | Meet the traffic design requirements | email | telephone | Team Celebration
381 | Traffice Design B | Ted Martin | (909) XXX-XXXX | Positive feedback on plans | email | telephone | Team Celebration
391 | Freeway Systems | Nigel Gallagher | (909) XXX-XXXX | Constructability | email | telephone | Team Celebration
392 | Electrical Operations | Samer Anssari | (909) XXX-XXXX | Electrical systems in place | email | telephone | Team Award
396 | Electrical Design B | Frank Ortiz | (909) XXX-XXXX | Meet electrical design requirements | email | telephone | Team Celebration
400 | Right of Way | Jose Ferrer | (909) XXX-XXXX | RW Certification | email | telephone | Team Award
529 | Field Construction | Kelly Flake | (909) XXX-XXXX | Construction per design | in-basket | telephone | District Director Recognition
External
Local Government | SBd Co Transportation | Larry Floyd | (909) XXX-XXXX | Public Support | telephone | cell phone | Team Celebration
U.S. Government | Bureau of Land Management | Patty Zhu | (909) XXX-XXXX | Stay involved until project is complete | email | U.S. Mail | Team Celebration